# CivicCast Standalone Adoption Plan

# CivicCast Standalone Adoption Plan, v1.4-v1.7

Status: draft operating plan Created: 2026-05-30 Current baseline: v1.3.1 private beta Windows installer proof Target: v1.7 announcement and early adoption readiness

## Purpose

This plan turns the current standalone CivicCast target list into four focused development releases. It intentionally excludes CivicSuite integration, broad governance/adoption logistics, and hardware work that CivicCast cannot directly ship in software. It keeps the software work required to become a serious open-source alternative for public meetings, community media, worship/nonprofit streaming, and PEG-style channel operations.

The v1.7 bar is not “everything forever.” The v1.7 bar is: a nontechnical station can install CivicCast, prove core publication paths, operate meetings and channel-style programming, recover from common failure modes, understand legal/procurement posture, and invite early adopters without making claims the software has not proven.

## Baseline: What v1.3.1 Already Proves

v1.3.1 is the private beta installer finish release.

- GitHub Release .exe is the preferred installer artifact.

- Checksum verification passed on the Windows tester.

- Windows installer, runtime launch, and first-run setup passed.

- First admin, recovery kit, storage bootstrap, private rehearsal, resident preview, backup/restore rehearsal, and support bundle passed.

- Provider lanes remain fail-closed unless proven.

- Public distribution, signing posture, live external-provider proof, granular roles, full restore, update/rollback, linear-channel operations, and connected TV platform support remain ahead.

## Release Strategy

The next four releases should each produce a release artifact, release notes, proof evidence, and a clear claim boundary.

| Release | Public framing | Core outcome |
| --- | --- | --- |
| v1.4 | Operations beta | Provider proof workflow and role-aware operations |
| v1.5 | Resilience beta | Full restore, update/rollback, and stronger quality gates |
| v1.6 | Channel and CTV beta | Cablecast-style software channel operations and Roku/reference CTV support |
| v1.7 | Early adoption candidate | Public-facing docs, procurement/legal posture, support intake, and adoption-ready proof bundle |

## Non-Goals Across All Four Releases

- Hosted or managed CivicCast service.

- CivicSuite integration.

- Enterprise SSO.

- Claims of broad public fediverse interoperability before target-instance proof exists.

- Claims of SDI, DeckLink, or headend hardware compatibility before partner proof exists.

- Silent cloud fallback for AI or provider lanes.

- Rewriting working modules just to match the spec’s future multi-repo topology.

## v1.4: Operations Beta

### Goal

Turn the v1.3.1 installer-first private beta into an operations beta by proving selected external provider lanes and separating common station responsibilities inside the operator console.

### Required Outcomes

- Controlled provider proof lane.

  - Choose a first live-provider proof set from Internet Archive, local NAS, YouTube private/unlisted, email/webhook notifications, podcast feed discovery, and ActivityPub target-instance proof.

  - Record redacted durable evidence for each live pass.

  - Keep unproven providers out of release claims.

- Provider proof workflow.

  - Setup and System Health guide operators from “credentials saved” to “controlled proof passed.”

  - Include prove now, retry, skip, rotate, stale-proof warning, and redaction review paths.

  - Show plain-English operator errors.

- Granular local roles.

  - Add setup/admin, meeting operator, records clerk, publish operator, and support/admin roles.

  - Enforce roles in backend routes and visible UI actions.

  - Keep read-only handoff views where helpful.

- Observed beta walkthroughs.

  - Run at least one nontechnical operator walkthrough.

  - Run at least one technical-admin walkthrough.

  - Convert friction into product fixes, documentation fixes, or regression tests before release.

### Likely Work Areas

- civiccast/auth/

- civiccast/installer/

- civiccast/publish/

- civiccast/schedule/

- civiccast/apps/portal-operator/

- civiccast/apps/portal-public/

- tests/installer/

- tests/publish/

- operator Playwright tests

- docs and release evidence

### v1.4 Exit Criteria

- At least one external provider proof set passes from a controlled live run.

- Provider readiness remains fail-closed until proof evidence exists.

- Secret leakage review passes for provider proof and support artifacts.

- Backend role enforcement tests pass for touched staff APIs.

- Operator-console tests cover at least one restricted role workflow.

- Docs clearly distinguish credentials configured, proof pending, proof passed, skipped, failed, and stale proof states.

## v1.5: Resilience Beta

### Goal

Make CivicCast resilient enough for real station operation by proving full restore, safe update, rollback, and broader quality gates.

### Required Outcomes

- Full restore proof.

  - Backup DB, media, config, station profile, schedules, captions, records, publish state, and credential metadata.

  - Restore into an isolated station profile.

  - Verify restored admin state, portal state, media playback, captions, records, publish status, and provider readiness.

  - Clearly report anything intentionally excluded or requiring re-entry.

- Safe update path.

  - Detect available update package or update source.

  - Run pre-update checks and backup/checkpoint.

  - Apply update.

  - Run post-update safe-to-broadcast proof.

  - Block broadcast when update proof fails.

- Rollback path.

  - Select rollback asset.

  - Execute rollback.

  - Verify restored runtime and safe-to-broadcast state.

  - Preserve operator-readable logs and support bundle context.

- Quality gate expansion.

  - Keep first-meeting journey green.

  - Add restore and rollback regression coverage.

  - Add provider proof workflow tests from v1.4 into the required gate.

  - Add accessibility and public-portal cross-browser/mobile checks where feasible.

  - Add secret-leakage scans for proof reports, restore reports, and support bundles.

### Likely Work Areas

- civiccast/installer/

- civiccast/db/

- civiccast/assets/

- civiccast/publish/

- civiccast/apps/portal-operator/

- tests/installer/

- tests/integration/

- release evidence and operator recovery docs

### v1.5 Exit Criteria

- Full restore into an isolated profile passes and is documented.

- Update apply proof passes or fails safely with clear operator messaging.

- Rollback proof passes from at least one controlled failed-update scenario.

- Support bundle captures restore/update/rollback context without secrets.

- Required quality gate list is updated and enforced for future releases.

## v1.6: Channel And CTV Beta

### Goal

Build the software pieces required for Cablecast-style channel operation and connected TV reach, while leaving physical headend, SDI, DeckLink, and Comcast delivery proof to partner validation.

### Required Outcomes

- Linear channel profiles.

  - Support one or more station channels, such as public, education, and government channel equivalents.

  - Store channel identity, branding, programming rules, output settings, and fallback behavior.

- Schedule-to-playout workflow.

  - Schedule live sources, file playback, slates, bulletin boards, reruns, and fallback blocks.

  - Handle gaps, underruns, and source failure with operator-visible states.

  - Produce now/next status per channel.

- Channel proof logs.

  - Record what was scheduled, what actually played, and what failed over.

  - Export operator-readable and machine-readable proof logs.

  - Attach captions/sidecars where available.

- Software outputs.

  - Support feasible software outputs such as HLS, RTMP, SRT, or NDI-style command planning where licensing permits.

  - Avoid claiming hardware compatibility until partner proof exists.

- Roku/reference CTV support.

  - Provide a stable public feed/API for live channels and VOD.

  - Build a Roku reference app or shippable prototype.

  - Support live HLS, VOD playback, captions, station branding, predictable content IDs, and browse/search by meeting, series, date, body, or topic.

  - Document the path for later Fire TV, Apple TV, and Android TV work.

### Likely Work Areas

- civiccast/cable/

- civiccast/live/

- civiccast/vod/

- civiccast/schedule/

- civiccast/cg/

- civiccast/apps/portal-public/

- civiccast/apps/

- tests/cable/

- tests/live/

- tests/vod/

- channel operations docs

### v1.6 Exit Criteria

- At least one end-to-end channel schedule can play through live/file/slate or equivalent software states.

- Channel now/next and proof logs are visible to operators.

- Failure/fallback behavior is tested.

- Public feed/API can drive the Roku/reference CTV surface.

- Roku/reference app can browse and play at least live channel and VOD content from CivicCast test data.

- Documentation states exactly what is software-proven and what requires partner station hardware validation.

## v1.7: Early Adoption Candidate

### Goal

Make CivicCast ready to announce for early adopters without overclaiming: downloadable, supportable, explainable, legally/procurement-legible, and backed by a coherent proof bundle.

### Required Outcomes

- Public release posture.

  - Decide public download path.

  - Resolve Windows signing or explicit unsigned-beta policy.

  - Provide a public install page that does not require private collaborator access.

  - Provide SmartScreen and WSL2 expectation language.

- Support intake.

  - Provide a public support intake path for non-collaborators.

  - Define what logs/support bundles users should attach.

  - Define response expectations for early adopters.

- Procurement and legal language.

  - Procurement language for CivicCast as open-source civic infrastructure.

  - Apache 2.0 and CC BY 4.0 explanation.

  - Data ownership and export language.

  - Public-records retention guidance with a clear non-legal-advice disclaimer.

  - Accessibility posture.

  - AI caption/summary disclaimer language.

  - Release policy and security reporting language.

  - Vendor replacement comparison language, especially Cablecast-style cost and lock-in framing.

- Proof bundle.

  - Consolidate installer proof, provider proof, restore proof, update/rollback proof, channel/CTV proof, and known limitations.

  - Make proof easy to read from README, docs index, release notes, and release assets.

- Early-adopter docs.

  - Quickstart.

  - Operator manual.

  - Technical admin manual.

  - Recovery guide.

  - Provider setup guide.

  - Channel operations guide.

  - CTV/Roku guide.

  - Known limitations and support boundaries.

### Likely Work Areas

- README.md

- CHANGELOG.md

- docs/

- docs/spec/

- docs/releases/

- docs/tester/

- civiccast/installer/

- public/operator docs surfaces

- release scripts and evidence checks

### v1.7 Exit Criteria

- Public download and trust posture are documented and tested.

- Early adopters can install without private repo access.

- Release notes and known limits avoid unproven claims.

- Proof bundle is complete enough for a technical station partner to evaluate.

- Procurement/legal docs are plain-English and institution-readable.

- Support intake works for someone outside the core repo.

- v1.7 can be announced as an early adoption candidate, not as a finished enterprise appliance replacement.

## Cross-Release Quality Bar

Every release should include:

- Updated release plan.

- Release evidence page.

- Known limitations update.

- Secret leakage scan over evidence and support artifacts.

- Targeted backend tests.

- Relevant Playwright/operator journey tests.

- Docs link check or equivalent manual proof.

- Installer smoke rerun if installer, runtime bootstrap, first-admin setup, or packaging changes.

- Clear release claim boundary.

## Suggested Agent Pipeline Run Order

- 2026-05-30-standalone-adoption-roadmap

  - Scope: convert this plan into validated pipeline manifests and release scope locks.

  - Output: accepted roadmap, v1.4 manifest, and release-level scope locks.

- v1.4 implementation run.

  - Scope: provider proof workflow and role-aware operations.

- v1.5 implementation run.

  - Scope: full restore, update/rollback, and quality gates.

- v1.6 implementation run.

  - Scope: channel operations and Roku/reference CTV.

- v1.7 implementation run.

  - Scope: public release posture, docs, support intake, and proof bundle.

## Immediate Next Actions

- Review this plan and decide whether v1.3.2 remains separate or folds into v1.7 public release posture.

- Complete and validate the Agent Pipeline manifest for the v1.4 implementation run.

- Select the first live provider proof set for v1.4.

- Decide which role gets implemented first and which workflow proves it.

- Identify the smallest isolated restore target for v1.5 planning.

- Identify Longmont Public Media channel-operation assumptions that can be represented in software before hardware validation.